## Sheet1
22nd |  | 29th | 5th | 12th | 19th | 26th | 3rd | 10th | 17th | 24th | 31st | 7th | 11th
sep |  | sep | nov | nov | nov | nov | dec | dec | dec | dec | dec | jan | jan
documention |  | documention | documention | documention | documention | documention | documention | documention | documention | buffer | buffer | buffer | submission
2dhd |  | concept art | finilaized enviroment concept | design document | design document | design document | design document | design document | design document |  |  |  | design document
backup |  | character | if have time explained | finalized character concept | asset list | prototyping | prototyping | prototying | general
ui |  | environment | design document | finilazed enemy design | prototyping | particle effects | particle effects | bugs and balancing | final playtest
must have explained |  | enemy | character concept art | sound exploration | implement gameplay into block out | balancing/playtesting | balancing/playtesting | implement animations | implement animations
basic story |  | could of have explained | enemy concept | prototyping | enemy implemention | finilizing ui elements | modeling | starting adding asset to level | implement models
prototyping |  | design document | ui style guide/ concept art | enemy | polish ui | modeling | asset list | particle effects | bug fixes
platforms | platforms | mood boards | floormap for lvl 1 | mock up ui | modeling | asset list | texturing | modeling | modelling
lock and key | lock and key | prototyping | story/lore document | level 1 blockout | lantern | texturing | asset list | asset list | asset list
collectibles | collectibles | platforms | prototyping | modeling | character model | character model | sound | texturing | texturing
|  | ui mock up in engine | sanity | character model | sound | lantern | sfx | asset list | asset list
|  | lantern | enemy |  | sourcing | sound | animtion | sound
|  |  | health |  |  | implement bgm | basic movement | polishing
[6 empty] | starting adding sfx |  | animation
[6 empty] | character model |  | hurt
[6 empty] | rigging/weight painting |  | complex movement